Appendix 6 – Detailed list of contracts

| Contract name | Contract amount and currency (taxes included) | Type of contract | Type of competition) | Procurement procedure | Selection method | Review by AFD | Specific Procurement Notice Publication date | Bid or Proposal Opening date | Contract signing date | Contract completion date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SPREP Kiwa GESI strategy | Projected: EUR 12 500. | C | IPC | REOI | QCBS | PRIOR | 26/02/22 | 26/02/2022 | To take place in May 2022 | June 2022 |
| CReME TA support: Cook Islands | Projected : / Actual: EUR 8 850. | C | IPC | RQ | QCBS | PRIOR | Not an open tender process | 16/02/2022 | 24/03/2022 | 14 April 2022 |
| CReME TA support: Tuvalu | Projected: / Actual : EUR 8 477 | IC | IPC | RQ | QCBS | PRIOR | Not an open tender process | 17/02/2022 | 26/03/2022 | 14 April 2022 |
| CReME TA support: Niue | Projected: / Actual: EUR 8 185 | C | IPC | RQ | QCBS | PRIOR | N/A | 23/02/2022 | 23/03/2022 | 14 April 2022 |
| Training programme – NbS and EbA for climate change adaptation (Activity 1.1.1) | Projected € 72,500. Actual. Difference. | C | IPC | REOI | QCBS | PRIOR | November 2021 | December 2021 | January 2022 | March 2023 |
| Support programme – Mainstreaming NbS into regional, national and local policies (Activity 1.1.2) | Projected € 60,000. Actual. Difference. | C | IPC | REOI | QCBS | PRIOR | October 2023 | December 2023 | January 2024 | September 2024 |
| Communications (Activity 1.2) | Projected € 10,500 | C | IPC | REOI | QCSB | PRIOR | July 2022 | August 2022 | September 2022 | March 2025 |
| Sustainability programme - sustainable finance mechanisms with countries involved in regional projects (Activity 3.1.2) | Projected € 38,000. Actual. Difference. | C | IPC | REOI | QCBS | PRIOR | January 2024 | March 2024 | April 2024 | October 2024 |
| Development of a database on NbS for Climate Change adaptation in the Pacific (Activity 3.1.2) | Projected € 16,800. Actual. Difference. | C | IPC | REOI | QCBS | PRIOR | October 2022 | November 2022 | December 2022 | April 2023 |
| Publication services | Projected TBD Actual Difference | IC | NPC | REOI | QCBS | PRIOR | January 2022 | February 2022 | March 2022 | March 2025 |
| Translation services (EN/FR) | Projected € 55,000. Actual. Difference. | IC | IPC | REOI | QCBS | PRIOR | January 2022 | March 2022 | April-May 2022 | October 2024 |
| Interpretation services (EN/FR, physical and online) | Projected € 26,000. Actual. Difference. | IC | IPC | REOI | QCBS | PRIOR |  |  | During meetings |  |
| External Audits | Projected € 18,000. Actual. Difference. | IC | IPC | RQ | FBS | / | September 2022 | October 2022 | November 2022 | March 2025 |

C for consulting services; IC for individual consultants; W for works; G for goods; P for Plants; NC for non-consulting services.

NPC: national procurement competition; IPC: international procurement competition.

For goods, works, plants and non-consulting services: PQL+IB: Prequalification and Invitation for Bids; IB: Invitation for Bids; RQ: Request for Quotations; DC: Direct Contracting.

For consulting services: REOI: Request for Expression of Interest; RQ: Request for Quotations; DC: Direct Contracting.

For consulting services: QCBS: Quality and Cost Based Selection; QBS: Quality Based Selection; FBS: Fixed Budget Based Selection; LCS: Least Cost Based Selection.

For goods, works, plants and non-consulting services, the contract should be awarded to the qualified bidder whose bid is technically substantially compliant and is the lowest evaluated bid; other selection method shall require prior approval from AFD.

Decision to carry out Post reviews requires AFD’s prior approval.